# Investment Committee: minutes

Meeting held on 15 July 2026.

## Present

Chair of the Investment Committee; Head of Investments; Investment Manager; Risk Officer.

## Matters considered

The Committee reviewed the model portfolios against the investment policy and agreed the actions below.

## Actions

| Ref | Action | Owner | Due | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| A-2026-07-01 | Replace Fenwick Strategic Multi-Asset in the Cautious portfolio with a lower-cost multi-asset fund. | Investment Manager | 30 September 2026 | In progress | Shortlist of three alternatives presented. |
| A-2026-07-02 | Reduce Tarn Property Securities in the Balanced portfolio to no more than 6%. | Investment Manager | 30 September 2026 | Completed |  |
| A-2026-07-03 | Review provider fee schedules for all multi-asset funds held. | Head of Investments | 31 December 2026 | Open |  |
| A-2026-07-04 | Notify the Committee if any portfolio's quarterly return is below -5.0%. | Investment Manager |  | Standing | Standing instruction. |